## Sheet1
Acitve - In Progress
Active - Pending
0 | Assigned to Normal Operations
Completed
Duplicate
Removed

## Goals and Objectives List
Goal | Objective Number | Objective | Coordinating Emergency Support Function | Supporting Emergency Support Functions | Start Date | End Date | Status (Dropdown List) | Comments
Goal 1: Reduce opioid misuse and abuse. | 1 - 4.1 | By August 1, 2018, consider options for utilizing community paramedics to deliver education on opioids including proper use, handling and disposal of prescription medication to those 55 and older. | 4 |  | 12.18.17 | 6.18.18 | Completed | The need described in this objective is being met by Human Services, so it was agreed that this Objective can be removed.
| 1 - 6.1 | By August 31st, 2018, the Student Support Advocate (SSA) program will contact 6,000 students identified as high risk for chemical dependency or mental health issues. 3,000 of those students will engage in full case management, and approximately 430 will be connected to and engaged in substance use disorder services by the SSA’s. | 6 |  | 11.6.17 |  | In Progress
| 1 - 6.2 | By June 30th, 2018, Continua Consulting Group will provide consultation services in 18-20 schools equipping staff with Trauma-Informed knowledge and skills to improve effectiveness in working with all children, and especially children who have been/are directly impacted by trauma and Adverse Childhood Experiences. This could result in impacting approximately 11,222 elementary, middle and high school students. | 6 |  | 11.6.17 | 2.5.18 | Completed
| 1 - 6.3 | By December 31, 2017, all 14 Senior Centers will have provided education on opioids including proper use, handling and disposal of prescription medication to those 55 and older attending those senior centers. | 6 | 8 | 11.6.17 | 12.6.17 | Completed
| 1 - 6.4 | During the calendar year 2018, Snohomish County Human Services will: • Maintain the naloxone supply for 21 Law Enforcement Agencies and their staff. • Continue training as needed for 21 Law Enforcement Agencies to keep current and new staff trained in administering naloxone. • Provide quarterly naloxone trainings to the public. | 6 |  | 11.6.17 |  | In Progress
| 1 - 6.5 | During the calendar year 2018, Snohomish County Embedded Social Workers (ESW) will provide assertive outreach and engagement to homeless individuals living in encampments. Through this program: • 120 individuals will be connected to detox. • 110 individuals will complete detox. • 120 individuals will complete a chemical dependency assessment. • 80 individuals will complete treatment. • 65 individuals will be connected to housing. | 6 | 13 | 11.6.17 |  | In Progress
| 1 - 6.6 | During the calendar year 2018, provide assessment, education and planning to 288 inmates to access Medication Assisted Treatment (MAT) upon release. Of the total inmates served, 40% will engage in medication assistance team upon release. | 6 | 13 | 11.6.17 |  | In Progress
| 1 - 6.7 | By budget year, 2019, deploy an Office of Neighborhoods Team (2 social workers, 1 Sheriff’s deputy, 1 Marysville police officer and 1 Arlington police officer) to provide direct outreach to vulnerable and homeless populations to serve North Snohomish County. | 6 | 13 | 12.6.17 |  | Incomplete | PENDING RESOURCE NEEDS
| 1 - 6.8 | By December 1, 2017, develop condensed training for fire districts to provide education on opioids including proper use, handling and disposal of prescription medication to those 55 and older. (Based on 1-6.3) | 6 |  | 11.30.17 | 12.1.17 | Completed
| 1 - 6.9 | By February 28th, 2018, the Human Services Department’s Opioid Outreach Specialist will partner with Marysville Fire District and South Snohomish County Fire and Rescue to develop a formal referral process by which Fire/EMS staff can send clients who have been revived from an opioid overdose to the Specialist for connection to treatment. | 6 |  | 2.5.18 | 2.28.18 | Completed
| 1 - 6.10 | By March 9th, 2018, the Human Services Department will create and share data definitions for the data collected by the Office of Neighborhoods and ESW’s. This work will guide how other jurisdictions collect data related to their embedded social workers so that the information is standardized across the county. | 6 |  | 2.5.18 | 3.9.18 | Completed
| 1 - 6.11 | By July 31, 2018, the Human Services Department will collaborate with Workforce Snohomish and the public workforce development system to develop an opioid education strategy with measurable outcomes for dislocated workers. | 6 |  | 2.5.18 |  | Completed | Date change
| 1 - 6.12 | By December 31, 2018, maintain training and education on opioids including proper use, handling and disposal of prescription medication to those 55 and older attending all 14 Senior Centers. |  |  | 2.5.18 |  | In Progress | Objective designed to maintain the work from 1-6.3
| 1 - 6.13 | By June 15, 2018, five additional schools will be selected to receive consultation services from Continua Consulting Group to equip staff with trauma-informed knowledge and skills to improve effectiveness in working with all children and adolescents. With the addition of five schools, a total of 22 schools in Snohomish County will be adhering to trauma-informed practices. | 6 |  | 5.21.18 | 6.15.18 | Completed | Final numbers were 6 additional schools for a total of 23.
| 1 - 8.1 | Distribute 500 prescription lock bags at community outreach events by March 31, 2018. | 8 |  | 11.6.17 | 6.30.18 | Completed
| 1 - 8.2 | Identify age appropriate school curriculum options for opioids/heroin education by March 31, 2018. | 8 |  | 11.6.17 |  | Completed
| 1 - 8.3 | Identify at least one school district willing to pilot the curriculum no later than the 2018-19 school year. | 8 |  | 11.6.17 |  | In Progress
| 1 - 8.4 | Expand syringe exchange program by 25% by June 30, 2018. | 8 |  | 11.6.17 |  | Incomplete | PENDING RESOURCE NEEDS (SHD is not considering combining with the syringe exchange program at this time)
| 1 - 8.5 | Increase pounds of medicine returns by 15% by December 31, 2018. | 8 |  | 11.6.17 |  | In Progress | May be revised
| 1 - 8.6 | Increase providers prescribing suboxone by 10% by November 1, 2018. | 8 |  | 11.6.17 |  | In Progress
| 1 - 8.7 | Reduce average wait time to enter opioid treatment programs (methadone, buprenorphine or other treatments) to less than 30 days by November 1, 2018. | 8 |  | 11.6.17 |  | In Progress
| 1 - 8.8 | By December 31, 2018, reduce opioid overdose deaths by 10 percent. | 8 |  | 11.6.17 |  | In Progress
| 1 - 8.9 | By December 31, 2018, partner with one school district in Snohomish County to host a community opioid awareness and prevention forum targeted toward youth and their families. | 8 |  |  |  | In Progress
| 1 - 8.10 | Develop a comprehensive list of providers in Snohomish County who are waivered for suboxone by August 30, 2018. | 8 |  |  |  | In Progress
| 1 - 8.11 | Hold at least one focus group of providers waivered for suboxone to determine level of preferred patient load and barriers to increasing load by October 31, 2018. | 8 |  |  |  | In Progress
| 1 - 8.12 | Complete training on all recommended opioid prevention curriculum by August 31, 2018 | 8 |  | 5.7.18 |  | In Progress | May be revised
| 1 - 8.13 | Host a train-the-trainer session for at least 15 educators on opioid prevention curriculum by November 30, 2018 | 8 |  | 5.7.18 |  | In Progress
| 1 - 8.14 | Develop materials for pharmacies to give clients informing them on the risks of prescription opioids, by August 30, 2018 | 8 |  | 5.7.18 |  |  | Changed date from end of July to end of August. (JMD 8.2.18 1529)
| 1 - 8.15 | Work with local pharmacies to begin selling prescription lock bags/boxes in the store by September 30, 2018 | 8 |  | 5.7.18 | 6.18.18 | Completed
| 1 - 8.16 | Develop best practices/guidelines document for pharmacists to follow when filling opioid prescriptions, by August 30, 2018 | 8 |  | 5.7.18 |  | In Progress
| 1 - 8.17 | Survey medium to large insurance companies that serve Snohomish County to determine coverage of medicine lock products, by September 30, 2018 | 8 |  | 6.27.18 |  | In Progress
| 1 - 8.18 | Work with at least 2 insurance companies and/or flex plan programs to begin allowing medicine lock products either through medical insurance or through FSA, by December 31, 2018 | 8 |  | 6.27.18 |  | In Progress
| 1 - 8.19 | Host a training on October 9th, 2018, in partnership with Economic Alliance of Snohomish County on substance use in the workplace and what employers can do. | 8 |  | 7.2.18 |  | In Progress
| 1 - 13.1 | By March 31, 2018, Diversion Center will provide 44 beds to address opioid addicted illnesses. | 13 |  | 11.6.17 | 1.29.18 | Completed
| 1 - 13.2 | Create a weekly report from the Snohomish County jail that tracks the number of inmates who test positive in booking for opiates, the number of inmates turned away from the jail for drug issues, and the number of inmates per week on a withdrawal watch by 5/31/2018. | 13 |  | 11.6.17 | 1.29.18 | Completed
| 1 - 13.3 | By February 28, 2018, convene a stakeholder group to identify potential wraparound services (including family and individual follow-up within 24 hours) for overdose victims who were administered naloxone. | 13 |  | 12.6.17 | 2.28.18 | Completed
| 1 - 15.1 | Within 30 days of being implemented, compile and disseminate a comprehensive list of Drug Take Back locations in Snohomish County. | 15 |  | 11.6.17 | 11.13.17 | Completed
| 1 - 15.2 | Moved to Goal 4 (4-15.1)
| 1 - 15.3 | By January 30, 2018, compile and disseminate a list of addiction treatment services available to residents of Snohomish County. | 15 |  | 11.6.17 | 1.29.18 | Completed
| 1 - 15.4 | By March 31, 2018, develop communication and dissemination plan for addiction treatment services available to residents and public safety personnel of Snohomish County. | 15 |  | 12.6.17 | 4.16.18 | Completed
Goal 2: Lessen the availability of opioids. | 2 - 8.1 | Educate 100 Snohomish County physicians on best practices in pain control by June 30, 2018. | 8 |  | 11.6.17 | 6.30.18 | Completed
| 2 - 8.2 | Hold at least one focus groups with pharmacists by June 30, 2018. | 8 |  | 11.6.17 | 6.30.18 | Completed
| 2 - 8.3 | Hold at least one focus groups with dentists, by September 30th, 2018 | 8 |  | 5.1.18 |  | In Progress | Meeting set for June 23, 2018 Meetng was cancelled due to no attendance. On agenda for Dental Society meeting in September. Date pushed back to end of September (JMD 7.16.18 1647)
| 2 - 8.4 | Hold at least one focus groups with veterinarians, by September 30, 2018. | 8 |  |  |  | In Progress
| 2 - 13.1 | By Nov 30, 2018, identify and prosecute pharmacies committing opioid prescription fraud. | 13 | 15 | 11.6.17 |  | Incomplete | PENDING RESOURCE NEEDS
Goal 3: Reduce criminal activity associated with opioids. | 3 - 13.1 | By December 31st, 2018 Snohomish County law enforcement agencies will identify system to track opioid related crimes. | 13 |  | 11.6.17 |  | In Progress | Date changed to 12/31/18 on July 2nd, 2018 (JMD 7.3.18 1117)
Goal 4: Use data to detect, monitor, evaluate, and act. | 4 - 4.1 | By January 31, 2018 secure authorization to identify and extract existing aggregate FirstWatch data related to opioid contacts. | 4 |  | 12.6.17 | 2.5.18 | Completed
| 4 - 4.2 | By December 31, 2018 consider need and options to integrate FirstWatch and ODMap data into single reporting structure. | 4 | 13, 6 | 12.6.17 |  | In Progress | PENDING NEW LANGUAGE (emailed Shaughn to get confirmation on new language) JMD 7.5.18 1406
| 4 - 4.3 | By March 31, 2018, identify cost and timeline for implementation of FirstWatch countywide. | 4 |  | 1.8.17 | 3.31.18 | Completed
| 4 - 5.1 | By November 1, 2017 establish a data collection committee comprised of representatives from ESFs 4, 6, 8, & 13 that will identify all data sets being used by stakeholders and by December 31, 2017 identify best option to provide a layered data set that optimizes the use of available data. | 5 | 8 | 11.6.17 | 1.8.17 | Completed
| 4 - 5.2 | By January 31, 2018, develop a dissemination process that provides available data to all stakeholders. | 5 | 7,8 | 11.6.17 | 1.31.18 | Completed
| 4 - 5.3 | By July 31, 2018, develop multi-jurisdictional essential elements of information that support critical coordination functions and metrics amongst local jurisdictions connected with the County's MAC group. | 5 |  | 2.5.17 |  | In Progress | Extended due date
| 4 - 5.4 | By July 31, 2018, develop common terminology for overlapping opioid response operations by County departments, local agencies, and local jurisdictions (e.g. embedded social workers, nuisance properties). | 5 |  | 2.5.17 | 5.7.18 | Completed | Extended due date. / Will need to create a new objective to reflect ongoing communciation with terminology (JMD 8.6.18 15:16)
| 4 - 5.5 | By December 31, 2018, coordinate the development of estimated, macro-level impact of opioid epidemic on Snohomish County. | 5 |  | 2.5.17 |  | Incomplete | PENDING RESOURCE NEEDS
| 4 - 5.6 | Through November 19, 2018, continue to coordinate data collection committee meetings and provide monthly updates on data collection status and needs. Through November 19, 2018, continue to coordinate data collection committee meetings and provide monthly updates on data collection status and needs. | 5 |  | 5.7.18 |  | In Progress
| 4-5.7 | By November 1, 2018, identify Snohomish County specific trends and characteristics in opioid overdose victims. | 5 |  | 8.3.18 |  | In Progress
| 4-5.8 | By November 1, 2018, identification of overdose trends, identify opportunities to more effectively target services to individuals who overdose. | 5 |  | 8.3.18 |  | In Progress
| 4-5.9 | By January 1, 2019, develop method to identify individuals who touch multiple opioid support services including EMS, law enforcement, hospitals, non-profits, and human services programs. | 5 |  | 8.3.18 |  | In Progress
| 4-5.10 | By November 1, 2018, develop method to identify individuals who are deceased but have received opioid support services. | 5 |  | 8.3.18 |  | In Progress
| 4-5.11 | By January 1, 2019, use data identify method to analyze effectiveness of key wraparound services. | 5 |  | 8.3.18 |  | In Progress
| 4-5.12 | By November 1, 2018, overlay overdose locations with other available data sets (including nuisance properties, drug houses, etc.) to identify areas of concentrated overdoses. | 5 |  | 8.3.18 |  | In Progress
| 4-5.13 | By November 1, 2018, in coordination with ESF 15, develop heat map (within applicable and approved data standards) that identifies key characteristics of overdoses. | 5 |  | 8.3.18 |  | In Progress
| 4 - 8.1 | By January 31, 2018, determine MED-Project data request and reporting schedule. | 8 |  | 12.6.17 | 1.29.18 | Completed
| 4 - 8.2 | Host a county-wide 7-day point in time data collection event the week of July 9-15, 2018 and release publication of the summary/fact sheet by July 31, 2018. | 8 |  |  | 7.15.18 | Completed
| 4 - 8.3 | Develop a model that estimates the burden of opioid addiction/dependence using locally adapted CDC methods by August 30th, 2018. | 8 |  |  |  | In Progress | Changed date from July to end of August (JMD 8.6.18 15:07)
| 4 - 13.1 | By August 31, 2018, connect with all Law Enforcement Embedded Social Worker (LEESW) teams in Snohomish County and create standardized reporting methods. (Relates to objective 4-5.3) | 13 |  | 5.7.18 | 8.31.18 | In Progress
| 4 - 15.1 | By June 1, 2018, develop, compile, and disseminate Data Collection Committee data to the public via a website or online portal. | 15 |  | 11.6.17 | 5.16.18 | Completed | Date changed to June-1, 2018
Goal 5: Reduce collateral damage to the communities. | 5 - 3.1 | By May 1, 2018, develop training and implement sharps handling protocol for applicable County and agency staff, volunteers, and community members. | 3 | 8 | 11.6.17 | 5.7.18 | Completed
| 5 - 3.2 | By May 1, 2018, initiate a program that integrates sharps disposal with current solid waste management processes, practices, and contracts. | 3 | 8 | 11.6.17 | 5.7.18 | Completed
| 5 - 3.3 | By January 31, 2018, convene meeting of Snohomish County Planning and Development Services, Snohomish County Sheriff's Office, Snohomish Health District, and Snohomish County Public Works to discuss nuisance property processes. | 3 |  | 12.6.17 | 2.5.18 | Completed
| 5 - 3.4 | By July 1, 2018, expand the multi-disciplinary approach to nuisance properties in Snohomish County through a collaboration with Planning and Development Services, Snohomish County Sheriff's Office, Snohomish Health District, Prosecuting Attorney's Office and Snohomish County Public Works. | 3 |  | 12.18.17 |  | In Progress | Deputy to start this month. May revise wording for this objective. Emailed Matt Zybas to get new language or confirm current language (JMD 7.5.18 1409)
| 5 - 4.1 | By December 31, 2018, develop consolidated curriculum for instructing the general public on CPR/AED, antidote deployment, and tourniquet application. | 4 |  | 12.6.17 |  | In Progress | Trained 250 people
| 5 - 8.1 | By January 30, 2018, develop a protocol that ensures SHD will respond within one hour to any symptomatic environmental exposures to illicit drugs experienced by first responders or other public sector employees. | 8 |  | 11.6.17 | 1.29.18 | Completed
| 5 - 8.2 | By August 30, 2018, distribute 1000 needle cleanup kits to the community. | 8 |  | 11.6.17 |  | In Progress | 900+ kits distributed. Changed date from 6/30/18 to July 15, 2018 on July 2, 2018 (JMD 7.3.18 1119) 970+ Kits given out as of July 2, 2018 (JMD 7.3.18 1119) Date changed to July 30th, 2018 (JMD 7.12.18 1531) Changed ending date to August 30th, 2018 (JMD 8.2.18 1532)
| 5 - 8.3 | Identify current baseline levels of neonatal withdrawal syndrome within Snohomish County by May 31, 2018. | 8 |  | 11.6.17 | 5.31.18 | Completed
| 5 - 8.4 | Meet with Providence team by July 15, 2018 to identify strategies for neonatal withdrawal syndrome and reaching at-risk women. | 8 |  | 11.6.17 | 7.15.18 | Completed
| 5 - 8.5 | By March 31, 2018, convene tabletop exercise with Snohomish Regional Drug & Gang Task Force to test process for reporting and responding to symptomatic environmental exposures identified in 5 - 8.1. | 8 |  | 1.8.18 | 4.16.18 | Completed | This objective was removed on 5.7.18 because it was determined that this protocol was not necessary.
| 5 - 15.1 | By May 31, 2018, design and deploy a public information campaign regarding SHARP pick-up and disposal. | 15 | 8 | 11.6.17 | 5.31.18 | Completed
| 5 - 15.2 | Create and publish at least one video every 90 days through December 31, 2018. Old text: Post to the web by March 30, 2018 a series of videos and content that attempt to de-stigmatize opioid addiction and measure reach by number of video “views” and webpage “hits”. | 15 | 8 | 11.6.17 |  | In Progress | Amendment made at the May 7th 2018 meeting
Goal 6: Provide information about the response in a timely and coordinated manner. | 6 - 5.1 | By September 30, 2018, reconvene Snohomish County's Mayors and other elected officials to update them on the status of the MAC Group's work. | 15 |  | 11.6.17 | 11.1.17 | Completed | Deleted Objective due to duplicate efforts in 7-7.14
| 6 - 15.1 | By November 1, 2017, stand up a Joint Information Center (JIC) at the Emergency Coordination Center, which includes documenting JIC processes and procedures. | 15 |  | 11.6.17 | 11.1.17 | Completed
| 6 - 15.2 | Develop a communications/marketing plan for faith communities by July 1, 2018 – (This is an amendment to objective 6-15.2) Old wording: By May 31, 2018, develop a communications plan to implement the recommendations made by relevant stakeholders, Community Organizations Active in Disasters (COAD) and interfaith members that targets underrepresented and vulnerable communities. | 15 | 7 | 11.6.17 |  | Completed | Split objective in to 2 objectives: 6-15-16 and 6-15-17
| 6 - 15.3 | By November 1, 2017, establish a Joint Information System (JIS) incorporating public information officers (PIOs) from all affected sectors across Snohomish County, including public safety, schools, agency partners, and other stakeholders. | 15 |  | 11.6.17 | 11.1.17 | Completed
| 6 - 15.4 | By January 12th, 2018, develop an interagency communications plan that supports the accomplishments of all objectives and shares information across all ESFs and affected communities within Snohomish County. | 15 |  | 11.6.17 | 1.8.18 | Completed
| 6 - 15.5 | Merged under 6-15.4
| 6 - 15.6 | By January 31, 2018, convene a working group to identify a process to formalize a definition of “whole community” that applies to the opioid epidemic. | 15 |  | 12.6.17 | 1.29.18 | Completed
| 6 - 15.7 | By June 1, 2018 create a plan for content creation and curation for www.snohomishoverdoseprevention.com. Original Objective wording was: Ensure www.snohomishoverdoseprevention.com is maintained, to include recovery and treatment program options available in Snohomish County. | 15 |  |  | 5.16.18 | Completed | New -- An amendment to the original Objective
| 6 - 15.8 | By September 10, 2018 create a resource/reference card that provides easy-to-access information for inmates released from Snohomish County jails, emergency rooms and other high-risk populations. | 15 |  | 5.7.18 |  | In Progress
| 6 - 15.9 | By December 31, 2018 develop process to review effectiveness of resource/reference card given to released inmates, Emergency Room patients, and other high risk populations. | 15 |  | 5.7.18 |  | In Progress | Language changed on 7.16.18 to ensure the objective follows the SMART format.
| 6 - 15.10 | Pitch/distribute at least one news release and/or media opportunity that highlight MAC Group accomplishments, goals or objectives each month through December 31, 2018. | 15 |  | 5.7.18 |  | In Progress
| 6 - 15.11 | By June 4, 2018 draft final content for "10 Things" campaign. | 15 |  | 5.7.18 | 6.4.18 | Completed
| 6 - 15.12 | Implement "10 Things" campaign by June 15, 2018 through February 18, 2019. | 15 |  | 5.7.18 |  | In Progress
| 6 - 15.13 | Publish a Snohomish Overdose Awareness resource guide, in partnership with Sound Publishing, by August 31, 2018. | 15 |  | 5.7.18 |  | In Progress
| 6 - 15.14 | By June 30, 2018, develop a media/communications plan to accompany the 7-day point-in-time being done July 9-15. | 15 |  | 5.7.18 | 6.30.18 | Completed
| 6 - 15.15 | Host “Overdose Prevention Night” at the Everett Aquasox on Saturday, September 1, including tables and resources to feature the “10 Things” campaign. | 15 |  | 5.7.18 |  | In Progress
| 6 - 15.16 | Meet and consult with Snohomish County faith leaders to develop opioid education materials for their faith communities by September 15th, 2018 | 15 |  | 7.5.18 |  | In Progress | Changed date to 9.15.18 (JMD 8.6.18 15:18)
| 6 - 15.17 | Develop and launch opioid education materials for Snohomish County faith communities by January 1, 2019. | 15 |  | 7.5.18 |  | In Progress
| 7 - 5.1 | By December 1, 2017, compile a list of point of contacts for each ESF Coordinating and Supporting Representative. | 7 | 5 | 11.6.17 | 11.13.17 | Completed
| 7 - 5.2 | By August 31, 2018, develop and provide recommendations for structuring the continued response to Snohomish County's opioid epidemic. |  |  | 5.7.18 |  | In Progress
| 7 - 6.1 | By August 30th, 2018, create and convene a workgroup under ESF 6, to develop objectives and identify responsible parties for each objective to plan/provide temporary/emergency shelter as indicated for individuals impacted by the opioid crisis. | 6 |  | 5.16.18 |  | In Progress | Changed to end of August from July (JMD 8.6.18 15:09)
| 7 - 6.2 | By November 1, 2018- Human Services will pursue the removal of the 850 patient cap per opiate substitution treatment program that was authorized through County Council Motion 16-508 on January 18, 2017. (NEW) | 6 |  | 6.20.18 | 7.16.18 | Completed
| 7 - 7.1 | By November 30, 2018 identify resources (funds, staff, time) already in use in order to accurately capture the amount of spending done countywide on opioid response. | 7 |  | 11.6.17 |  | In Progress
| 7 - 7.2 | By January 30, 2018, develop a review process that provides resources as expeditiously as practicable. | 7 |  | 11.6.17 | 1.30.18 | Completed
| 7 - 7.3 | By November 1, 2017, assign a point of contact in each department under the Snohomish County Executive to respond to requests received by the workgroup participants. | 7 |  | 11.6.17 | 11.1.17 | Completed
| 7 - 7.4 | By March 31, 2018, integrate county-wide opioid related legislative priorities into LobbyGov. | 7 |  | 12.6.17 | 1.23.18 | Completed
| 7 - 7.5 | By March 31, 2018, convene a meeting of relevant stakeholders, Community Organizations Active in Disasters (COAD) and interfaith members to discuss barriers to securing addiction services and support, as well as methods to reach underrepresented and vulnerable communities. | 7 |  | 12.6.17 | 3.31.18 | Completed
| 7 - 7.6 | Merged with 7 - 7.5
| 7 - 7.7 | By March 31, 2018, identify need and appropriate process to engage transit and para-transit providers. | 7 |  | 12.6.17 | 4.16.18 | Completed
| 7 - 7.8 | By November 30, 2018, Snohomish County and partnering agencies and jurisdictions will identify potential funding resources/mechanisms for resource requests received by ESF 7 and/or DEM. | 7 |  | 2.5.18 |  | In Progress
| 7 - 7.9 | By February 21, 2018, The Snohomish County Executive’s Office will provide MAC Group members proposed criteria for objectively reviewing, prioritizing, and funding resource requests. | 7 |  | 2.5.18 | 2.21.18 | Completed
| 7 - 7.10 | By March 19, 2018, MAC group members will review, comment, amend, and agree to, criteria (proposed in 7 – 7.9) for objectively reviewing, prioritizing, and funding resource requests. | 7 | All | 2.5.18 | 3.19.18 | Completed
| 7 - 7.11 | By July 1, 2018 identify service and treatment providers that are willing to establish a 24/7 resource network to assist first responders and law enforcement embedded social worker teams that respond to opioid related calls that do not result in transport to hospital emergency rooms. | 7 | 4, 13 | 2.5.18 | 6.18.18 | Completed | 7-7.11 is being revised and combined with 7 - 7.12 (NOW , 7-7-17)
| 7 - 7.12 | By July 1, 2018 collaborate with representatives from EMS, law enforcement, and Snohomish County 911 to outline a process in which Snohomish County 911 will possess a master list of service providers and will notify the public safety entity requesting services of which service provider to contact. | 7 | 4, 13 | 2.5.18 | 6.18.18 | Completed | 7-7.12 is being revised and combined with 7 - 7.11 (NOW , 7-7-17)
| 7 – 7.13 | September 1, 2018, The City of Everett and Snohomish County Executive’s Office will partner on working with the Puget Sound Regional Council (PSRC) to expand the Regional Reduced Fare Permit program to include individuals with substance use disorder and remove barriers to accessing the program. | 7 |  | 5.7.18 | 6.18.18 | Completed | Partnered with Everett and Community Transit and agreed to purchase 60 low fare cards. The cards will be distributed to clients of the office of Neighborhoods teams.
| 7 - 7.14 | By September 30, 2018, the Snohomish County Executive’s Office will convene a second meeting of mayors and tribal leaders to provide an update on the MAC Group’s work, discuss opportunities for partnership, and determine level of interest and support beyond November 30, 2018. | 7 |  | 5.7.18 |  | In Progress
| 7 – 7.15 | By June 5, 2018, Solicit input from Snohomish DEM, Snohomish County Human Services, and faith community leaders to begin development of para-navigator training to be used by faith communities in their response to issues including the opioid epidemic, sheltering, and emergency preparedness and response. | 7 |  | 5.7.18 | 6.18.18 | Completed
| 7 – 7.16 | By July 1, 2018, identify priority requests to state and federal legislators in support of the county’s response to the opioid epidemic, as agreed to by the MAC Group. | 7 |  | 5.7.18 |  | Completed | The MAC group will review the Washington State Opioid Response Plan and provide consolidated feedback identifying aligned interests and potential funding sources. (Comments due to Nate Marti by June 22nd)
| 7 - 7.17 | By Oct 1st, 2018 – Establish a six-month pilot program to connect law enforcement (SCSO), Fire Departments (with Community Paramedic resources), and Human Services in order to provide post opioid overdose outreach to increase engagement with those who are at elevated risk of experiencing a fatal opioid overdose. The team will provide follow-up outreach to measure success 1) reduce overdose-related deaths, 2) reduce repeated overdoses, 3) increase the support network for survivors and families, and 4) help overdose victims get into treatment. This objective references those overdose-related calls originating beyond the scope of work that is actively occurring with the Office of Neighborhoods/Human Services (embedded social workers). | 7 |  | 6.27.18 |  | In Progress | New language as of 7.5.18

## Data Points (hidden)
Completed | ESF
Ongoing | 3
Incomplete | 4
In Progress | 5
6
7
8
10
13
15

## Sample Weekly Action Plan (hidden)
DRAFT Consolidated Action Plan for Week Ending ?????
Task # | Task Name | Lead | Start Date | End Date | Comms | Comments/Status
MISSION 1: Make an additional 200+ safer living spaces available
1.1 | Document daily shelter vacancies as outreach resource | J Watson/ Adrienne Easter (HSD), 3/1
1.2 | Setting up of new safe sleeping options
1.2.2 | Accelerate opening of the three Bridging the Gap authorized encampments encampments |  |  |  | x
1.2.2.3 | Aurora Site (Licton Springs Village)
1.2.2.3.1.5 | Contact LIHI daily | Jen Chwalibog (HSD) |  | 2017-03-27 |  | Completed
1.2.2.3.4 | Form Community Advisory Council (CAC) | Tom Van Bronkhorst (DON) | 1900-01-01 | 2017-04-28
1.2.2.3.4.4 | Schedule CAC first meeting | Tom Van Bronkhorst (DON), LIHI |  | 2017-04-24
1.2.2.3.5.2 | Complete building tiny houses | LIHI |  | 2017-04-28
1.2.3 | Set –up Navigation Center | M Ashbrook (FAS)/ Jess Chow (HSD)
1.2.3.1.6 | Identify permanent location for Operation Nightwatch | Jason Johnson (HSD) |  | 2017-05-01
1.2.3.4 | Open Navigation Center | Genie Sheth (HSD), REACH |  | 2017-06-02
1.2.3.4.3 | Building becomes available for occupancy | Mike Ashbrook (FAS) |  | 2017-05-20
1.2.4 | Accelerate opening the Bridging the Gap Indoor Shelter
1.2.4.2 | Implement Community Outreach Plan
1.2.4.2.4 | Follow-up and Report Back
1.2.4.2.4.2 | Update outreach email list | Tara Beck (HSD) |  | 2017-04-27
1.2.4.2.4.3 | Prepare, review and distribute meeting notes to attendees | Tara Beck (HSD), Compass |  | 2017-04-28
1.2.4.2.4.5 | Determine if CAC is needed | Compass; HSD |  | 2017-04-28
1.3 | Develop and launch services as part of the Navigation Center and Team deployment | (HSD) |  | 2017-05-01
1.3.3.3 | Hold second community meeting | Jason Johnson (HSD), Jess Chow (HSD) |  | 2017-04-24
1.3.4.3 | Develop pet management plan | Genie Sheth (HSD) |  | 2017-04-24
1.3.5 | Establish protocols for referrals, interventions, etc. for Navigation Team and Downtown Emergency Service Center (DESC) team | J Chow, others (HSD) |  | 2017-04-17
1.3.7 | Assess existing gaps in the service and housing options available for the Navigation Team and Center | Adrienne Easter, Dusty Olson (HSD) |  | 2017-04-27
1.3.9 | HSD Contract is executed | Genie Sheth (HSD) |  | 2017-04-24
1.3.9.1 | Management plan completed | Genie Sheth (HSD) |  | 2017-04-24
1.4 | Use the EOC activation as a catalyst for the By-Name-List (BNL) practice
1.4.1 | Continue BNL practice with long-term shelter stayers. | Dusty Olson and Lindsay Garrity (HSD) |  | 2017-04-28 |  | Ongoing